## work plan
# | Task Name | Assign Person | Est. Start Time | Est. End Time | Start Time | End Time | Report Person | Resources | Deliverables | Budget | Note | Status
1 | Họp chọn đề tài | Nhơn,Phụng | 2023-10-18 | 2023-10-18 | 2023-10-18 | 2023-10-18 | Nhơn |  | Dự báo thời tiết |  |  | Done
2 | Vẽ kiến trúc | Nhơn,Phụng | 2023-10-19 | 2023-10-19 | 2023-10-19 | 2023-10-19 | Nhơn | https://app.diagrams.net/#G1QZN1Azqiz9eziJAQmNf6XTxEUDhVZh9_ | Kiến trúc hệ thống |  |  | Done
3 | Workflow | Phụng, Nhơn | 2023-10-20 | 2023-10-22 | 2023-10-20 | 2023-10-22 | Phụng | https://app.diagrams.net/#G1QZN1Azqiz9eziJAQmNf6XTxEUDhVZh9_ | Workflow hệ thống hoạt động |  |  | Done
4 | Họp | Phụng, Nhơn | 2023-10-23 | 2023-11-23 | 2023-10-23 | 2023-10-23 |  |  | Thống nhất kiến trúc và workflow |  |  | Done
5 | Hợp nhất kiến trúc | Phụng, Nhơn | 2023-10-23 | 2023-11-23 | 2023-10-23 | 2023-10-23 |  | https://app.diagrams.net/#G1QZN1Azqiz9eziJAQmNf6XTxEUDhVZh9_ |  |  |  | Done
6 | Mockup | [6 empty] | https://docs.google.com/spreadsheets/u/1/d/1NTBVDMmiUesKkJ7VhR86QGSkL7CT9wPJq-iGI-ikHFI/edit?usp=drive_web&ouid=105151999270123026132 |  |  |  | Done
6.1 | Mockup GUI | Nhơn | 2023-10-23 | 2023-10-26 | 2023-10-23 | 2023-10-23 | Nhơn | https://docs.google.com/spreadsheets/u/1/d/1NTBVDMmiUesKkJ7VhR86QGSkL7CT9wPJq-iGI-ikHFI/edit?usp=drive_web&ouid=105151999270123026133 | Mô phỏng giao diện người dùng |  |  | Done
6.2 | M Reversion | Nhơn | 2023-10-23 | 2023-10-26 | 2023-10-23 | 2023-10-23 | Nhơn | https://docs.google.com/spreadsheets/u/1/d/1NTBVDMmiUesKkJ7VhR86QGSkL7CT9wPJq-iGI-ikHFI/edit?usp=drive_web&ouid=105151999270123026134 |  |  |  | Done
6.3 | M Tracking log | Nhơn | 2023-10-23 | 2023-10-26 | 2023-10-23 | 2023-11-20 | Phụng | https://docs.google.com/spreadsheets/u/1/d/1NTBVDMmiUesKkJ7VhR86QGSkL7CT9wPJq-iGI-ikHFI/edit?usp=drive_web&ouid=105151999270123026135 |  |  |  | Done
6.4 | M [control] control_data_file | Nhơn | 2023-10-23 | 2023-10-26 | 2023-10-24 | 2023-10-23 | Nhơn | https://docs.google.com/spreadsheets/u/1/d/1NTBVDMmiUesKkJ7VhR86QGSkL7CT9wPJq-iGI-ikHFI/edit?usp=drive_web&ouid=105151999270123026136 |  |  |  | Done
6.5 | M [control] control_data_file_configs | Nhơn | 2023-10-23 | 2023-10-26 | 2023-10-25 | 2023-10-24 | Nhơn | https://docs.google.com/spreadsheets/u/1/d/1NTBVDMmiUesKkJ7VhR86QGSkL7CT9wPJq-iGI-ikHFI/edit?usp=drive_web&ouid=105151999270123026137 |  |  |  | Done
6.6 | M [Staging] WeatherData | Phụng | 2023-10-23 | 2023-10-26 | 2023-10-29 | 2023-10-29 | Phụng | https://docs.google.com/spreadsheets/u/1/d/1NTBVDMmiUesKkJ7VhR86QGSkL7CT9wPJq-iGI-ikHFI/edit?usp=drive_web&ouid=105151999270123026138 |  |  |  | Done
6.7 | M [Staging] load_WeatherData | Phụng | 2023-10-23 | 2023-10-26 | 2023-10-29 | 2023-10-29 | Phụng | https://docs.google.com/spreadsheets/u/1/d/1NTBVDMmiUesKkJ7VhR86QGSkL7CT9wPJq-iGI-ikHFI/edit?usp=drive_web&ouid=105151999270123026139 |  |  |  | Done
6.8 | M [dw] fact_weather | Phụng | 2023-10-23 | 2023-10-26 | 2023-10-29 | 2023-10-29 | Phụng | https://docs.google.com/spreadsheets/u/1/d/1NTBVDMmiUesKkJ7VhR86QGSkL7CT9wPJq-iGI-ikHFI/edit?usp=drive_web&ouid=105151999270123026140 |  |  |  | Done
6.9 | M [dw] dim_weather_code | Phụng | 2023-10-23 | 2023-10-26 | 2023-10-29 | 2023-10-29 | Phụng | https://docs.google.com/spreadsheets/u/1/d/1NTBVDMmiUesKkJ7VhR86QGSkL7CT9wPJq-iGI-ikHFI/edit?usp=drive_web&ouid=105151999270123026141 |  |  |  | Done
6.10 | M [dw] dim_date | Phụng | 2023-10-23 | 2023-10-26 | 2023-10-29 | 2023-10-29 | Phụng | https://docs.google.com/spreadsheets/u/1/d/1NTBVDMmiUesKkJ7VhR86QGSkL7CT9wPJq-iGI-ikHFI/edit?usp=drive_web&ouid=105151999270123026142 |  |  |  | Done
6.11 | M [dw] aggregate_weatherdata | Nhơn | 2023-10-23 | 2023-10-29 | 2023-10-29 | 2023-10-29 | Nhơn | https://docs.google.com/spreadsheets/u/1/d/1NTBVDMmiUesKkJ7VhR86QGSkL7CT9wPJq-iGI-ikHFI/edit?usp=drive_web&ouid=105151999270123026143 |  |  |  | Done
6.12 | M [DataMart] weatherdata | Nhơn | 2023-10-23 | 2023-10-29 | 2023-10-29 | 2023-10-29 | Nhơn | https://docs.google.com/spreadsheets/u/1/d/1NTBVDMmiUesKkJ7VhR86QGSkL7CT9wPJq-iGI-ikHFI/edit?usp=drive_web&ouid=105151999270123026145 |  |  |  | Done
6.13 | M [DataMart] aggregate_weatherdata | Nhơn | 2023-10-23 | 2023-10-29 | 2023-10-29 | 2023-10-29 | Nhơn | https://docs.google.com/spreadsheets/u/1/d/1NTBVDMmiUesKkJ7VhR86QGSkL7CT9wPJq-iGI-ikHFI/edit?usp=drive_web&ouid=105151999270123026145 |  |  |  | Done
7 | Thiết kế database | [6 empty] | https://docs.google.com/spreadsheets/u/1/d/1NTBVDMmiUesKkJ7VhR86QGSkL7CT9wPJq-iGI-ikHFI/edit?usp=drive_web&ouid=105151999270123026146 |  |  |  | Done
7.1 | db Control | Nhơn | 2023-10-23 | 2023-10-28 | 2023-10-23 | 2023-10-28 | Nhơn | https://app.diagrams.net/#G1QZN1Azqiz9eziJAQmNf6XTxEUDhVZh9_ |  |  |  | Done
7.2 | db Statging | Phụng | 2023-10-23 | 2023-10-28 | 2023-10-23 | 2023-10-28 | Nhơn | https://app.diagrams.net/#G1QZN1Azqiz9eziJAQmNf6XTxEUDhVZh9_ | cấu trúc cơ sở dữ liệu |  |  | Done
7.3 | db data warehouse | Nhơn | 2023-10-23 | 2023-10-28 | 2023-10-23 | 2023-10-28 | Nhơn | https://app.diagrams.net/#G1QZN1Azqiz9eziJAQmNf6XTxEUDhVZh9_ | cấu trúc cơ sở dữ liệu |  |  | Done
7.4 | db data mart | Phụng | 2023-10-23 | 2023-10-28 | 2023-10-23 | 2023-10-28 | Phụng | https://app.diagrams.net/#G1QZN1Azqiz9eziJAQmNf6XTxEUDhVZh9_ | cấu trúc cơ sở dữ liệu |  |  | Done
8 | Data Maping | [10 empty] | Done
8.1 | M [Staging] WeatherData | Nhơn | 2023-10-28 | 2023-11-03 | 2023-10-28 | 2023-11-03 | [5 empty] | Done
8.2 | M [Staging] load_WeatherData | Phụng | 2023-10-28 | 2023-11-03 | 2023-10-28 | 2023-11-03 | [5 empty] | Done
8.3 | M [dw] fact_weather | Nhơn | 2023-10-28 | 2023-11-03 | 2023-10-28 | 2023-11-03 | [5 empty] | Done
8.4 | M [dw] dim_weather_code | Phụng | 2023-10-28 | 2023-11-03 | 2023-10-28 | 2023-11-03 | [5 empty] | Done
8.5 | M [dw] dim_date | Nhơn | 2023-10-28 | 2023-11-03 | 2023-10-28 | 2023-11-03 | [5 empty] | Done
8.6 | M [dw] aggregate_weatherdata | Phụng | 2023-10-28 | 2023-11-03 | 2023-10-28 | 2023-11-03 | [5 empty] | Done
8.7 | M [DataMart] weatherdata | Nhơn | 2023-10-28 | 2023-11-03 | 2023-10-28 | 2023-11-03 | [5 empty] | Done
8.8 | M [DataMart] aggregate_weatherdata | Phụng | 2023-10-28 | 2023-11-03 | 2023-10-28 | 2023-11-03 | [5 empty] | Done
9 | Coding |  | 2023-11-03 | 2023-12-01 | [7 empty] | Done
9.1 | Coding db Control | Nhơn | 2023-11-04 | 2023-11-09 | 2023-11-04 | 2023-11-09 |  |  | Tạo bảng và code sql |  |  | Done
9.2 | Coding db Statging | Phụng | 2023-11-04 | 2023-11-09 | 2023-11-04 | 2023-11-09 |  |  | Tạo bảng và code sql |  |  | Done
9.3 | Coding db data warehouse | Nhơn | 2023-11-04 | 2023-11-09 | 2023-11-04 | 2023-11-09 |  |  | Tạo bảng và code sql |  |  | Done
9.4 | Coding db data mart | Phụng | 2023-11-04 | 2023-11-09 | 2023-11-04 |  |  |  | Tạo bảng và code sql |  |  | Done
9.5 | Coding getAPIExtract.py | Nhơn | 2023-11-10 | 2023-12-01 | 2023-11-10 | [6 empty] | Done
9.6 | Coding loadToStaging.py | Phụng | 2023-11-10 | 2023-12-01 | 2023-11-10 | 2023-12-01 | [5 empty] | Done
9.7 | Coding tranformStagingToWarehouse.py | Phụng | 2023-11-10 | 2023-12-01 | 2023-11-10 | 2023-12-01 | [5 empty] | Done
9.8 | Khởi tạo server: host, port | Nhơn | 2023-11-10 | 2023-12-01 | 2023-11-10 | 2023-12-01 | [5 empty] | Done
9.9 | Coding loadWarehouseToServer.py | Nhơn | 2023-11-10 | 2023-12-01 | 2023-11-10 | 2023-12-01 | [5 empty] | Done
9.10 | Coding UI | Phụng | 2023-11-10 | 2023-12-01 | 2023-11-10 | 2023-12-01 | [5 empty] | Done
9.11 | Deploy UI | Nhơn | 2023-11-10 | 2023-12-01 | 2023-11-10 | 2023-12-01
10 | Testing | [10 empty] | Done
10.1 | Testing Extract.py | Phụng | 2023-12-01 | 2023-12-08 | 2023-12-01 | 2023-12-08 | [5 empty] | Done
10.2 | Testing loadStaging.py | Nhơn | 2023-12-01 | 2023-12-08 | 2023-12-01 | 2023-12-08 | [5 empty] | Done
10.3 | Testing tranformStagingToWarehouse.py | Nhơn | 2023-12-01 | 2023-12-08 | 2023-12-01 | 2023-12-08 | [5 empty] | Done
10.4 | Testing loadWarehouseToServer.py | Phụng | 2023-12-01 | 2023-12-08 | 2023-12-01 | 2023-12-08 | [5 empty] | Done
10.5 | Testing UI | Nhơn | 2023-12-01 | 2023-12-08 | 2023-12-01 | 2023-12-08 | [5 empty] | Done
11 | Document &PPT | [10 empty] | Done
11.1 | Data feed specificaiton | Phụng | 2023-12-09 | 2023-12-14 | 2023-12-09 | 2023-12-14 | [5 empty] | Done
11.2 | Maping data | Nhơn | 2023-12-09 | 2023-12-14 | 2023-12-09 | 2023-12-14 | [5 empty] | Done
11.3 | Server specification | Phụng | 2023-12-09 | 2023-12-14 | 2023-12-09 | 2023-12-14 | [5 empty] | Done
11.4 | Report doc | Phụng | 2023-12-09 | 2023-12-14 | 2023-12-09 | 2023-12-14 | [5 empty] | Done
11.5 | Report slide | Nhơn | 2023-12-09 | 2023-12-14 | 2023-12-09 | 2023-12-14 | [5 empty] | Done